# SaaS Migration Technical Runbook

This document summarizes the technical plan to convert the existing training site into a multi-tenant SaaS platform where each training institute can sign up and manage its own students, courses, and billing.

## Executive Summary

Goal: Convert the existing training site into a multi-tenant SaaS so different training institutes can create and manage their own students, courses, and billing.

Outcome: A self-serve platform with tenant isolation, recurring billing, and admin tools for support and reporting.

## Assumptions

App is Laravel-based (PHP) with MySQL and S3-style storage.

Current payments use Paystack for one-off registration; we will add Stripe (recommended) for subscriptions or keep Paystack recurring where regionally required.

## Phases & Steps

Phase 0 — Discovery (2–4 days): inventory models/tables/controllers; produce table→model→controller mapping.

Phase 1 — Tenancy scaffold (shared-schema) (2–3 weeks): create Tenant model + migrations; add nullable tenant_id to core tables; implement TenantAware trait with global Eloquent scope; ResolveTenant middleware (subdomain/org slug); CLI helpers; update controllers to use tenant scoping; add tests.

Phase 2 — Billing & subscriptions (1–2 weeks): install Stripe + Laravel Cashier; add billing fields to tenants; implement checkout/subscription, webhook handlers; billing UI or use Stripe Billing Portal; migrate or coexist with Paystack for legacy flows.

Phase 3 — Onboarding & admin UI (2–3 weeks): public signup → create tenant + admin user; tenant dashboard (settings, team invites, billing, usage); quotas enforcement and notifications.

Phase 4 — Data migration & rollout (1–2 weeks): create default tenant; backup DB; migration script to set tenant_id on existing rows; test in staging; make tenant_id non-nullable after verification.

Phase 5 — Testing, CI/CD & staging (1–2 weeks): unit, integration, E2E tests; GitHub Actions for CI (phpunit, static analysis); staging deploy and smoke tests.

Phase 6 — Operations & monitoring (ongoing): backups, Sentry, APM, centralized logs, uptime monitoring, runbooks.

Phase 7 — Enterprise features (later): SAML/SCIM SSO, per-tenant DB option, custom domains, SLA and dedicated support.

## Key Data Model Changes (concrete)

Add `tenants` table: id, name, slug, stripe_customer_id, stripe_subscription_id, status, settings (json), timestamps.

Add `tenant_id` to core tables: lms_courses, lms_modules, lms_materials, lms_students, lms_enrollments, lms_tracks, lms_scheduled_classes, lms_certificates, payments, training_registrations.

Create `Tenant` model and `TenantAware` trait (global scope) and `ResolveTenant` middleware.

## Billing Strategy (simple)

Use Stripe + Laravel Cashier for subscriptions, trials, invoices, webhooks. Keep Paystack for legacy one-offs or migrate to Stripe.

Store provider IDs on `tenants` (stripe_customer_id, stripe_subscription_id) and update billing_status via webhooks.

Secure webhook verification and do not store card numbers.

## Migration Plan (safe)

1. Add nullable tenant_id columns and create `default` tenant.

2. Back up DB and run migration script to set existing rows' tenant_id to the default tenant.

3. Deploy middleware and TenantAware in read-only mode; validate in staging.

4. After verification, make tenant_id non-nullable and enforce strict scoping.

## Testing & QA (must-have)

Unit tests for TenantAware scopes and billing logic.

Integration tests for signup -> tenant creation -> subscription -> create course -> enroll flows.

E2E tests for full happy paths using Cypress or Playwright.

## Security & Compliance (simple checklist)

HTTPS everywhere, HSTS, CSP.

Webhook and API signature verification.

GDPR endpoints: data export and deletion for tenants.

Secrets in environment/secret manager (no .env in repo).

## CI/CD & Infra

GitHub Actions: run PHP CS Fixer, PHPStan, phpunit on PRs.

Environments: dev, staging, prod. Use managed platform (Render, DigitalOcean App Platform, or Laravel Vapor).

Storage: S3-compatible for media. Backups: nightly DB dumps + retention.

## Estimated Team & Timeline

Team: 1–2 backend devs (Laravel), 1 frontend/designer part-time, 1 devops part-time, 1 QA part-time.

MVP timeline: 6–10 weeks total depending on team size and parallel work.

## Immediate Next Steps

Approve 2–4 day discovery audit to produce a detailed file-by-file list and firm cost estimate.

Decide on primary payment provider (Stripe recommended) or confirm local provider requirement.

If approved, run automated repo audit and scaffold Tenant model, middleware, and a migration to add tenant_id columns.

Generated by an automated script. Review content and adjust timelines based on team availability.